## Sheet1
| Name of Project? | Conduit Forum Application
| Project cost estimation | 76250 | €
| Project Manager | Menom Haque
| Date | 2022-03-01
Role | Name | Milestone | Gate 0 |  | Gate 1 | Gate 2 |  | Gate 3 | [6 empty] | Gate 4 |  | Gate 5
|  | Estimate | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | SUM |  | Hour Cost |  | Total Cost |  | Usage Ratio
Project Manager and Control | Menom Haque | 100 | 20 | 20 | 20 | [7 empty] | 20 |  |  | 20 |  | 100 | h |  | h | 0 | € | 100 | %
Key Account Manager | Mirva "Mforce" Porkka | [16 empty] | 0 | h |  | h | 0 | € | #DIV/0! | %
Senior Project manager | Arnold "Juggernaut" Suksi | [16 empty] | 0 | h |  | h | 0 | € | #DIV/0! | %
Back End programming | Matti "Urali" Urri | 150 |  |  | 20 | 35 | 35 | 40 | 10 | [6 empty] | 10 |  | 150 | h | 75 | h | 11250 | € | 100 | %
Front End programming | Kauno Koivisto | 200 | [5 empty] | 10 |  |  | 30 | 30 | 40 | 40 | 50 |  |  | 200 | h | 75 | h | 15000 | € | 100 | %
Service Support | Heli "HeHe" Heikkinen | 30 |  |  | 5 | 5 |  | 5 | [7 empty] | 5 | 10 | 30 | h | 80 | h | 2400 | € | 100 | %
Customer Service | Heikki Halipula | 25 |  |  |  | 5 |  | 10 | [7 empty] | 10 |  | 25 | h | 80 | h | 2000 | € | 100 | %
Graphic Design / UX | Purho "Grapizza" Kekkonen | 50 | [5 empty] | 10 | 10 |  | 10 | 10 | 10 |  |  |  |  | 50 | h | 70 | h | 3500 | € | 100 | %
Service Design | Maija Keskinen | 50 | [9 empty] | 10 | 10 |  | 10 | 10 | 10 | 50 | h | 80 | h | 4000 | € | 100 | %
Software Testing | Klaus Kähö | 50 | [5 empty] | 15 | [7 empty] | 15 | 20 | 50 | h | 70 | h | 3500 | € | 100 | %
Security/Penetration Testing | Mauno Kara | 50 | [12 empty] | 30 |  | 20 | 50 | h | 70 | h | 3500 | € | 100 | %
Architect/Chief Programmer | Carola "Cake" Kettunen | 150 | 20 | 20 | 35 | 20 | [9 empty] | 25 | 30 | 150 | h | 100 | h | 15000 | € | 100 | %
DevOps Expert | Reino "Stackker" Kasa | 30 | [9 empty] | 5 | 5 | 5 | 5 | 10 |  | 30 | h | 70 | h | 2100 | € | 100 | %
| Resource 1 | 2500 | 500 | 1000 | 1000 | [12 empty] | 2500 | unit | 1 | unit | 2500 | € | N/A | %
| Resource 2 | 2000 | [5 empty] | 1000 | 1000 | [8 empty] | 1000 | unit | 1 | unit | 1000 | € | N/A | %
| Resource 3 | 2000 | [12 empty] | 1000 |  | 1000 | 2000 | unit | 1 | unit | 2000 | € | N/A | %
| Other Cost 1 | 1500 | 500 |  |  | 500 |  | 500 | [9 empty] | 1500 | unit | 1 | unit | 1500 | € | N/A | %
[17 empty] | Total Work Cost |  | 69250 | €
[17 empty] | Other Costs |  | 7000 | €
[17 empty] | Total Cost |  | 76250 | €